## Sheet1
Category | Task | Description | Status | Owner | Notes
Core Functionality | Audio Capture Works | Verify audio capture works across speakers/headphones/HDMI devices | Completed
Core Functionality | Device Switching | Automatically detect output device changes and restart loopback capture | Completed
Core Functionality | Pause/Resume Listening | Implement pause and resume without destroying audio session | Completed
Core Functionality | Stop Listening | Ensure all timers + STT services correctly shut down | Completed
Transcription Pipeline | Clean Transcript Deduplication | Ensure no repeated utterances appear in the transcript list | In Progress
Transcription Pipeline | Timestamp Integrity | Ensure all utterances have correct timestamps | Not Started
Transcription Pipeline | Transcript Storage | Save cleaned transcript in DB or local storage | Not Started
AI Features | Suggestion Engine | UserQuestion, RecentUtterances, Memory, and RAG all producing good results | Completed
AI Features | Rolling Summaries | Every 10–15 seconds summaries update cleanly without duplicates | Completed
AI Features | RAG Document Upload | Upload PDF/DOCX, embed, store, retrieve relevant chunks | Completed
AI Features | RAG Ranking Quality | Ensure cosine similarity ranking returns good top-k chunks | Completed
User Experience | Start/Pause/Stop UI | UI must reflect real listening state | Completed
User Experience | Live Transcript Panel | Display live transcript in a readable way | Completed
User Experience | Suggestion Output UI | Clean formatted output panel for AI suggestions | Completed
User Experience | Settings Page | Audio device selection + app options + toggles | Not Started
User Experience | Notifications | Toast notifications for pause, resume, errors | Not Started
User Experience | Loading Indicators | Show spinners for Gemini and RAG operations | Not Started
Stability Testing | Headphone Switching Test | Switch between speakers/headphones multiple times | Not Started
Stability Testing | Network Weak Signal Test | Simulate poor internet and ensure app recovers | Not Started
Stability Testing | Gemini Failure Handling | Gracefully handle Gemini timeouts/errors | Not Started
Stability Testing | Deepgram Errors | Retry logic & fallback for STT dropouts | Not Started
Stability Testing | Long Meeting Test | Run for 2 hours without crash or memory leak | Not Started
Security | API Key Storage | Ensure keys are stored in backend config/env only | Not Started
Security | HTTPS Only | Ensure all API endpoints are served via HTTPS | Not Started
Security | Document Sanitization | PDF/DOCX sanitized before text extraction | Not Started
Security | Authentication | Secure backend endpoints using JWT | Not Started
Data Management | Transcript Export | Allow export to text, markdown, or PDF | Not Started
Data Management | Memory Persistence | Store rolling summaries per meeting | Not Started
Data Management | Local Cache Cleanup | Clear old logs/temp files after sessions | Not Started
Data Management | Log File Output | Generate logs in %AppData%/AppName/logs | Not Started
Branding & Polish | App Icon | Provide a professional app icon (.ico) | Not Started
Branding & Polish | Color Theme | Use consistent theme throughout the UI | Not Started
Branding & Polish | Splash Screen | Optional small loading splash window | Not Started
Branding & Polish | App Name & Branding | Finalize name + product branding assets | Not Started
Deployment | Generate MSIX Installer | Build MSIX installer for Windows deployment | Not Started
Deployment | Auto-Update Mechanism | Squirrel/MSIX auto-updates | Not Started
Deployment | Test on Clean Machine | Install on a PC without Visual Studio | Not Started
Deployment | Versioning Strategy | Use semantic versioning (v1.0.0) | Not Started
Deployment | Release Notes | Prepare a clean release notes file | Not Started
Deployment | Licensing (Optional) | Define app license if needed (MIT/Proprietary) | Not Started